## WeekFeb6
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Weekly Group Meeting - Discuss development plan | Group | 30 minutes | 2023-02-08 | 100 | 2023-02-08 | 30 minutes
Hardware Testing - Voice and Sound IO | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Set up Github repository | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Figure out GTTS (Google Text to Speech) | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class

## WeekFeb13
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Weekly Group Meeting - Discuss development plan | Group | 30 minutes | 2023-02-08 | 100 | 2023-02-08 | 30 minutes
Hardware Testing - Voice and Sound IO | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Set up Github repository | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Figure out GTTS (Google Text to Speech) | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class