## WeekFeb6
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Weekly Group Meeting - Discuss development plan | Group | 30 minutes | 2023-02-08 | 100 | 2023-02-08 | 30 minutes
Hardware Testing - Voice and Sound IO | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Set up Github repository | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Figure out GTTS (Google Text to Speech) | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Group Meeting after Friday Class (2/10/2023) | Group | 20 minutes | 2023-02-10 | 100 | 2023-02-10 | 30 minutes

## WeekFeb13
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Find module to do input | Brandon | ~ 3 hours | 2023-02-15 | 50 | TBD - By Next meeting | 2 hours
LED Design output | Jack | ~ 2 hours | 2023-02-15 | 100 | 2023-02-17 | 2 hours
GTTS Output | Carson | ~ 2 hours | 2023-02-15 | 50 | TBD - By next meeting | 1.5 hours
Weekly Group Meeting | Group | ~ 30 minutes | 2023-02-15 | ----- | ----- | -----

## WeekFeb20
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Integrate visuals into main game structure | Jack | 2 hours | 2023-02-22 | 0 | *** | ***
Debug and incorporate audio into the game | Carson | 2 hours | 2023-02-22 | 0 | *** | ***
Finish proof of concept and start implementation | Brandon | 2 hours | 2023-02-22 | 0 | *** | ***
Group meeting on 2/22/23 - Discuss presentation | Group | 30-40 minutes | 2023-02-22 | *** | *** | ***
We've been able to develop our individual parts and have attempted to incorporate them into our main program structure. Jack was successful in developing the different right-left, hand-foot
combinations and now plans to implement them into the main game structure displaying the correct confirguration. Carson had successful audio tests and has minor bug fixes to look into. After that
he will start to fully implement the GTTS audio output into the program. Brandon researched voice-in modules and completed installation of one of the modules. Next Brandon is going to finish
proof of concept and start implementation into the main program.