## WeekFeb6
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Weekly Group Meeting - Discuss development plan | Group | 30 minutes | 2023-02-08 | 100 | 2023-02-08 | 30 minutes
Hardware Testing - Voice and Sound IO | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Set up Github repository | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Figure out GTTS (Google Text to Speech) | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Group Meeting after Friday Class (2/10/2023) | Group | 20 minutes | 2023-02-10 | 100 | 2023-02-10 | 30 minutes

## WeekFeb13
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Find module to do input | Brandon |  | 2023-02-15 | 0
LED Design output | Jack | ~ 2 hours | 2023-02-15 | 0
GTTS Output | Carson |  | 2023-02-15 | 0
Weekly Group Meeting | Group | ~ 30 minutes | 2023-02-15 | ----- | ----- | -----