## WeekFeb6
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Weekly Group Meeting - Discuss development plan | Group | 30 minutes | 2023-02-08 | 100 | 2023-02-08 | 30 minutes
Hardware Testing - Voice and Sound IO | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Set up Github repository | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Figure out GTTS (Google Text to Speech) | Group | In-class | 2023-02-10 | 100 | 2023-02-10 | In-class
Group Meeting after Friday Class (2/10/2023) | Group | 20 minutes | 2023-02-10 | 100 | 2023-02-10 | 30 minutes

## WeekFeb13
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Find module to do input | Brandon | ~ 3 hours | 2023-02-15 | 50 | TBD - By Next meeting | 2 hours
LED Design output | Jack | ~ 2 hours | 2023-02-15 | 100 | 2023-02-17 | 2 hours
GTTS Output | Carson | ~ 2 hours | 2023-02-15 | 50 | TBD - By next meeting | 1.5 hours
Weekly Group Meeting | Group | ~ 30 minutes | 2023-02-15 | ----- | ----- | -----

## WeekFeb20
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Integrate visuals into main game structure | Jack | 2 hours | 2023-02-22 | 70 | not complete | 1 hour
Debug and incorporate audio into the game | Carson | 2 hours | 2023-02-22 | tbd | not complete | 45 minutes
Finish proof of concept and start implementation | Brandon | 2 hours | 2023-02-22 | tbd | not complete | 1.5 hours
Group meeting on 2/22/23 - Discuss presentation | Group | 30-40 minutes | 2023-02-22 | 100 |  | 1 hour
We've been able to develop our individual parts and have attempted to incorporate them into our main program structure. Jack was successful in developing the different right-left, hand-foot
combinations and now plans to implement them into the main game structure displaying the correct confirguration. Carson had successful audio tests and has minor bug fixes to look into. After that
he will start to fully implement the GTTS audio output into the program. Brandon researched voice-in modules and completed installation of one of the modules. Next Brandon is going to finish
proof of concept and start implementation into the main program.

## WeekFeb27
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Continue to implement code visuals into main program | Jack | 2 hours | 2023-03-03 | 100 | *** | 1 hour
Solving bug errors/ new VO module | Carson | 2 hours | 2023-03-03 | 100 | *** | 1.5 hours
VI specific word bug and implementing module into code | Brandon | 2 hours | 2023-03-03 | 75 | *** | 2 hours
Group Meeting 3/3 | Group | 30 minutes | 2023-03-03 | *** | ***
Brandon made progress regarding the Voice Input controls and module. He completed a proof of concept regarding the module, but has some issues with detecting a word within a phrase of sentence, if not spoken slowly enough. He plans to investigate this issue, then to implement this component into our main program. Carson made progress in regard to the voice output. He has completed a proof of concept for the basic voice output, but has run into issues regarding implementation into the main program. These bugs he will be looking into, while also looking for other libraries that could bypass these issues. Jack has made progress by continuing to work on the visual display and implementing that into our main twister code making sure to line up the right command withe the right visual.

## WeekMar6
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Finish up implementation of voice input module | Brandon | 30 minutes | 2023-03-10 | *** | *** | ***
Clean and incorporate code into main structure | Brandon | 30 minutes | 2023-03-10 | *** | *** | ***
Brandon worked on the word bug and got far with implementing the voice input module. Carson was able to incorporate the voice output module into the main code while Jack worked on the visual display implementation.